## FEBRUARY TASKS
S/N | ACTIVITY | RESPONSIBLE PERSON | DUE DATE | STATUS
1 | Facilitate internet the back office team | MWAMINI | 16/02/2026 | ACHIEVED
2 | Full up on the letter sent to Tanesco concerning computers | LIGHTNESS | 16/02/2026 | ACHIEVED
3 | Report to be sent a day before weekly meeting so as each person can read | LIGHTNESS | 16/02/2026 | ACHIEVED
4 | Information on the total number of agents | LIGHTNESS | 16/02/2026 | ACHIEVED
5 | employment number | IDRIS | 16/02/2026 | ACHIEVED
6 | Prepare a letter of employment of 18 days to new agents for assurance | LAURYN | 16/02/2026 | ACHIEVED
7 | Make sure employees are registered to NSSF | LAURYN | 16/02/2026 | ACHIEVED
16/02/2026.
1 | Air cooler | MWAMINI | 24/02/2026 | ACHIEVED
2 | termination of employee | LAURYN | 24/02/2026 | ACHIEVED
3 | make sure agents handling time is not more that 3 mins | LIGHTNESS | 24/02/2026 | ACHIEVED
4 | make follow up of computers from Tanesco | LIGHTNESS | 24/02/2026 | ACHIEVED
24/02/2026
1 | aircooler to call centre office | MWAMINI | 2026-03-05 | ACHIEVED
2 | full up on the computers from Tanesco | WILLIAM | 2026-03-06 | ACHIEVED
3 | facilitation of a cupboard to the office | MWAMINI | 2026-03-07 | ACHIEVED
4 | sending and preparing of report on drop up of AHEEVA system | IDRIS | 2026-03-08 | ACHIEVED
2026-03-03
1 | appointment of each shift team leader | LIGHTNESS | 2026-10-03 | ACHIEVED
2 | payments to agents and operation stuff | MWAMINI | 2026-10-03 | ACHIEVED
1 | facilitation of ID to agents | HEMED AND LIGHTNESS | 17/03/2026 | ACHIEVED FIRST BATCH 100
| budget of agents uniform | LIGHTNESS | 17/03/2026 | ACHIEVED
3 | full up on the computers from Tanesco | LIGHTNESS | 17/03/2026 | ACHIEVED
4 | Installation of Biometric system | HEMED AND FRANK | 17/03/2026 | ACHIEVED
6 | distribution of contracts, policies and dressing timetable | LAURYN | 17/03/2026 | ACHIEVED
7 | invoice to Tanesco | HEMED AND LIGHTNESS | 17/03/2026 | ACHIEVED
| facilitation of probtion contract 19 days to new agents 36 | LIGHTNESS | 17/03/2026 | ACHIEVED
| agents returining of contracts | HAPPINESS | 24/03/2026 | ACHIEVED
| Agents attendance in percentage | HAPPINESS | 24/03/2026 | ACHIEVED
| Agents registration number in Biometric system | HEMEDI AND FRANK | 31/03/2026 | ACHIEVED
| facilitation of ID to agents | LIGHTNESS | 31/03/2026 | ACHIEVED
| sending of final agents number, TIN and NSSF number | HAPPINESS | 31/03/2026 | ACHIEVED
31/03/2026
| payment of agents salaries | WILLIAM AND MWAMINI | 2026-07-04 | ACHIEVED
14/04/2026
| Uniform payment | WILLIAM | 14/4/2026 | ACHIEVED
| facilitation of desktop | MWAMINI | 14/4/2026 | ACHIEVED
| impovement of weekly report editing, graph and quality assurance | HAPPINESS | 14/4/2026 | ACHIEVED
| talking to agents on arrival time to avoid over crowded on biometric system | HAPPINESS | 14/4/2026 | ACHIEVED
14/04/2026
| invoice to TANESCO | LIGHTNESS AND HEMED | 21/4/2026 | ACHIEVED
21/04/2026
| External cloud faciitation for backup payment | MWAMINI | 28/04/2026 | ACHIEVED
| Letter to Tanesco concering holiday payments | HEMED | 28/04/2026 | ACHIEVED
| back office proposal on Mei Mosi | LIGHTNESS AND HEMED | 28/04/2026 | ACHIEVED
28/04/2026
| Mei Mosi issue | WILLIAM AND BRIAN | 2026-05-05 | ACHIEVED
| incentives to agents | WILLIAM AND BRIAN | 2026-05-05 | ACHIEVED
| preparing of new excel of agents with NSSF number, NIDA and TIN number | HAPPINESS | 2026-05-05 | ACHIEVED
2026-05-05
| follow up on Payments | HEMED | 2026-12-05 | ACHIEVED
| invoice follow up | LIGHTNESS | 2026-12-05 | ACHIEVED
| payments of agents salaries | WILLIAM AND MWAMINI | 2026-12-05 | ACHIEVED
2026-12-05
| provision of emergence medical money | MWAMINI | 19/5/2026 | ACHIEVED
19/5/2026
26/05/2026
| meeting with Tanesco follow up | HEMED | 2026-02-06 | ACHIEVED
| making follow up on PAYE | LAURYN | 2026-02-06 | ACHIEVED
| making followup on payments | HEMED | 2026-02-06 | ACHIEVED
2026-02-06
| provision on first aid kit | MWAMINI | 2026-09-06 | ACHIEVED
| preparing and sending report to directors | HEMED | 2026-09-06 | ACHIEVED
| preparing invoice of payment | LIGHTNESS | 2026-09-06 | ACHIEVED
| payment to employees | WILLIAM AND MWAMINI | 2026-09-06 | ACHIEVED
| interview for new batch | HEMED AND LIGHTNESS | 2026-09-06 | ACHIEVED
| sending new batch for training | HEMED AND LIGHTNESS | 2026-09-06 | ACHIEVED
2026-09-06
| uniform to agents | LIGHTNESS AND MWAMINI | 16/6/2026 | ACHIEVED
| provision of contracts to back office team | MWAMINI | 16/6/2026 | ACHIEVED
| overtime to backoffice team | WILLIAM AND BRIAN | 16/6/2026 | ACHIEVED
ACHIEVED
| making followup on payments | HEMED | 23/6/2026 | ACHIEVED
23/6/2026
| payments of NSSF and PAYE of agents | WILLIAM AND MWAMINI | 30/6/2026 | ON PROGRESS
| holiday bonus to agents | WILLIAM AND BRIAN | 30/6/2026 | ON PROGRESS WAITING ONFEEDBACK ON THE MEETING WITH TANESCO
| Medical inusrance | LAURYN | 30/6/2026 | ON PROGRESS WAITING FOR PAYMENT OF AGENTS NSSF
| meeting with Tanesco director | WILLIAM AND BRIAN | 30/6/2026 | ON PROGRESS
| Implement monthly"Top 5" incentives | WILLIAM AND BRIAN | 30/6/2026 | ON PROGRESS
| hiring sales officer | WILLIAM AND BRIAN | 30/6/2026 | ON PROGRESS
| Meeting with TRA | HEMED | 30/6/2026 | PROSPONDED TILL JULY
| suggestion box | MWAMINI | 30/06/2026 | ON PROGRESS